## Slide 1
www.integranxt.com
Product plan– iWMS, iTracks
JAS'24 - Update
Review OND’24 Plan

## Slide 2
JAS '24 update- iWMS (Planned vs Actual)
Quarter | Category | Planned | Actual | Remarks
JAS'24 | On-time delivery(iWMS+iTracks) | 100% | 80% | Unplanned IAuthor LaTeX completed successfully. Delays in development of without Camunda
 | Budget value (iWMS + iTracks) | 160.32L (WMS and iTracks) | 63.73 (till August) | Due to Bloomsbury delay in sign off, the budget was underutilized.
Important Note: We have received an unplanned Product to be developed in this quarter (iAuthor LaTeX), for which we had to assign core developers to complete the development and testing.

## Slide 3: JAS'24 iWMS - Planned Delivery Goals
Customer | Platform Setup* |  | Testing (Prod.Tech.) | Testing (Customer) | Go Live Date | Why? | JAS'24 Status
WMS New onboarding | Start Date | End Date | End Date | End Date |  |  | 
ACS - iPE4.0 | 1-Jul-2024 | 20-Jul-2024 | 25-Jul-2024 | NA | 31-Jul-2024 28-sep-2024 YTD | Process improvement | Production UAT; feedback received for iPubEdit and WMS
Springer (Books) | 20-May-2024 | 13-Aug-2024 | 31-Aug-2024 | YTD | 05-Sep-24 12-Sep-24 30-Sep-24 | New customer transition; Springer | S5.S200,S300,S600, Completed- S650 stage dev completed
Springer Journals | 1-Jul-2024 | 10-Jul-2024 | NA | 12-Jul-2024 | 12-Jul-2024 | Customer requirement | Completed
WKH (Journals) - Enhancements | 1-Jul-2024 | 20-Sep-2024 | 30-Sep-2024 | NA | 6-0ct -2024 | Customer requirement | On Track
CUP (Journals) - Enhancements | 1-Jul-2024 | 20-Sep-2024 | 30-Sep-2024 | NA | 6-0ct -2024 | Customer requirement | On Track
KLI Pear Ease | 22-Jul-2024 | 20-Aug-2024 | 30-Aug-2024 | YTD | 9-Sep-2024 | Customer requirement to make 5 journal prod live | Moved out of JAS
Platform setup includes - Camunda Design, File IO Verification, Tools IO, Integration Module, Unit Testing

## Slide 4: JAS'24 iWMS - Planned Delivery Goals
Customer | Platform Setup* |  | Testing (Prod.Tech.) | Testing (Customer) | Go Live Date | Why? | JAS'24 Status
WMS New onboarding | Start Date | End Date | End Date | End Date |  |  | 
CUP (Journals) - Dashboard | 1-Aug-2024 | 17-Sep-2024 | NA | 24-Sep-2024 | 3-Oct-2024 | Customer requirement | Completed
New iTracks Integration | 1-Jul-2024 | 20-Sep-2024 | 30-Sep-2024 | NA | 6-Oct-2024 | To decommission old iTracks(Integration of productivity module | On Track
LS (Journals) | 1-July-24 | 28-Sep-24 | 10-Oct-24 | YTD | 18-Oct-24 30-Sep-24 13-Oct-24 | New customer transition; Elsevier | Customer Demo Provided , P2 points On Track
WKH Issue Workflow​ | 01-Jul-24​ | 20-Jul-24​ | 28-July-24 ​ | NA​ | 06-Aug-24​ 14-Sep-24​ 28-Sep-24​ 6-Oct-24 | Customer requirement​ | PAP stage is in PT UAT​ Issue Proof – T&E Signed off​ Issue Revises –Signed off ELD – in Defect fixing. Target: 18-Sep 3rd Oct; PT target: 20-Sep​ 5-Oct Elsevier customer visit; so, planning to move by 1 week; Non Camunda code to be merged; ​
ELS (Books) | YTP | YTP | YTP | YTP | YTP | New customer transition; Elsevier | Moved to OND
Platform setup includes - Camunda Design, File IO Verification, Tools IO, Integration Module, Unit Testing

## Slide 5
JAS'24 iWMS - Core feature milestones
S.No | Type | Milestone | Go Live Date | Total Effort in person days | Why ? | JAS'24 Status
1 | IALT | Implementation | 31-Jul-24 | 20 | New customer transition; Elsevier | Completed
2 | PeerEase – POC | WMS integration | 31-Jul-24 | 20 | Paid project: New customer | In client UAT
4 | Customized BPMN module | Address the limitation from Camunda | 28-Aug-24 | 50 | To address the limitation of Cammunda | Completed
5 | No-Code Platform | File Status - Journal code and issue name wise | 20-Aug-24 | 12 | To view all article status in by issue or journal code in single page | Completed
6 | No Code Platform | Master screen(Workflow configuration, IO configuration, custom tag configuration) | 15-Sep-24 | 40 | To Fast Track the implementation. Identified modules will be developed in this quarter | Completed
7 | No Code Platform | Production options | 20-Aug-24 20-Sep-24 | 15 | To fast track the testing, if there is any change in the intermediate activity. We can enable the particular activity and do the testing | On Track

## Slide 6
JAS'24 iWMS - Core feature milestone
S.No | Type | Milestone | Go Live Date | Total Effort in person days | Why ? | JAS'24 Status
8 | No-Code Platform | Switch WMS | 30-Aug-24 | 25 | Provide option for users to switch different WMS | Completed
9 | No-Code Platform | Tools upload for production tech | 05-Sep-24 | 20 | To provide provision for prodn. tech to upload the tools | Moved to OND(iAuthor LaTeX priority)
10 | No Code Platform | Tool IO – API To configure the API as adapter | 10-Sep-24 | 18 | Configuration module | Moved to OND(iAuthor LaTeX priority)
11 | No Code Platform | Reference Option | 28-Sep-24 | 14 | To download the worked files from data centre. | In Progress(On Track)
12 | No Code Platform | Menu configuration and access | 28-Sep-24 | 15 | To configure the menu and provide access to the user | Moved to OND (iAuthor LaTeX priority)
 |  |  |  | 249 |  | 

## Slide 7
www.integranxt.com
iWMS Review OND’24 Plan

## Slide 8
OND '24- Budget and Team Capacity (iWMS)
Budget | Planned
Budget Value (iWMS+iTracks ) | 162.95L
Budget Person days (WMS+iTracks) | 2003 days
IMPLEMENTATION TEAM |  |  | 
Role | Count (FTE) | Capacity (Person days) | REMARKS
Developers | 8.5 | 540 | Anandan ,Shanmugapriya, Venkat, Vaithiswaren, Magesh, Deebika, Chithiraikani, Srimathi,,Bosco, (Remarks – After mid of Nov'24 moved goes to Maternity leave )
SQA | 2 | 60 | Paul,Sooraj
Total Capacity (Dev and SQA) | 10.5 | 630 | 
Dev Lead/QA Lead | 1 | 60 | Dev Lead : Gnanamani, QA Lead :Murali
Implementation Lead | 2 | 120 | Neelakandan.G,Ramesh.G
Product Management |  |  | 
Architect |  |  | 
New WMS Admin | 2 | 120 | Dhanasekar, Varadharaj
Delivery Manager | 0.5 | 30 | Senthil Kumar
Grand Total | 16 | 960 | 

## Slide 9: OND'24 iWMS - Planned Delivery Goals
Customer | Platform Setup* |  | Testing (Prod.Tech.) | Testing (Customer) | Go Live Date | Why?
WMS New onboarding | Start Date | End Date | End Date | End Date |  | 
Elsevier Books | 1-Oct-2024 | 5-Nov-2024 | 13-Nov-2024 | NA | 15-Nov-2024 | New customer transition
Elsevier LeMan's | 1-Oct-2024 | 02-Dec-2024 | 10-Dec-2024 | NA | 13-Dec-2024 | New customer transition
Elsevier Conv Word | 10-Oct-2024 | 4-Dec-2024 | 11-Dec-2024 | NA | 13-Dec-2024 | New customer transition
Elsevier CPC | 20-Nov-2024 | 16-Dec-2024 | 16-Dec-2024 | NA | 20-Dec-2024 | New customer transition
Springer -Books | 1-Oct-2024 | 15-Nov-2024 | 20-Nov-2024 | NA | 22-Nov-2024 | New customer transition
Platform setup includes - Camunda Design, File IO Verification, Tools IO, Integration Module, Unit Testing

## Slide 10: OND'24 iWMS - Planned Delivery Goals
Customer | Platform Setup* |  | Testing (Prod.Tech.) | Testing (Customer) | Go Live Date | Why?
WMS New onboarding | Start Date | End Date | End Date | End Date |  | 
CUP (Journals) - Enhancements | 1-Oct-2024 | 20-Dec-2024 | 30-Dec-2024 | NA | 31-Dec-2024 | Customer requirement
Elsevier Latex P2 Points | 1-Oct-2024 | 5-Nov-2024 | 13-Nov-2024 |  | 15-Nov-2024 | Enhancement Points
WKH(Journals) - Enhancements | 1-Oct-2024 | 20-Dec-2024 | 30-Dec-2024 | NA | 31-Dec-2024 | Customer requirement
ACS (Journals) - Enhancements | 1-Oct-2024 | 20-Dec-2024 | 30-Dec-2024 | NA | 31-Dec-2024 | Customer requirement
IWMS Documentation preparation | 1-Oct-2024 | 20-Dec-2024 | NA | NA | 20-Dec-2024 | Technical, Testing and User documents
IWMS Testing Samples collection | 1-Oct-2024 | 21-Oct-2024 | NA | NA | 21-Oct-2024 | Testing Samples for the WMSes which are in live
Platform setup includes - Camunda Design, File IO Verification, Tools IO, Integration Module, Unit Testing

## Slide 11
OND'24- Core Team Capacity (iWMS)
CORE TEAM |  |  | 
Role | Team (FTE) | Capacity (Man days-OND'24) | Remarks (WMS)
Developers | 6 | 360 | (Vinoth, Mohanraj, Devanath, Karthick, Kalaiyarasi, Aravind)
Tester | 1 | 60 | 
Total Capacity (Dev and Testing) | 7 | 420 | 
Dev Lead/QA Lead | 0.25 | 15 | Rajkumar/Gnanamani
UI Developer | 0.5 | 30 | Naveen
Architect | 1 | 30 | Veera
Grand Total | 8.75 | 495 | 

## Slide 12
OND'24 iWMS - Core feature milestone
S.No | Type | Milestone | Planned Start Date | Planned End Date | Total Effort in PDs | Why ?
1 | Core | Batch File handling | 1-Oct-2024 | 31-Oct-2024 | 20 | This is required for Book building and Issue workflow
2 | Core | Checklist integration | 1-Oct-2024 | 31-Oct-2024 | 10 | This is a critical requirement from Production for validation and Verification
2 | Core | Generic Engine activity mapping | 1-Oct-2024 | 31-Oct-2024 | 25 | Engine Activities to be made configurable
3 | No code | Improve Tools IO configuration | 1-Oct-2024 | 31-Oct-2024 | 20 | Tools IO to be made configurable
4 | Core | Chaser Functionality | 1-Oct-2024 | 31-Oct-2024 | 20 | This is required for migration of existing workflows (email chaser and other chasing functionality)
5 | Core | Archival/Retrieval | 1-Nov-2024 | 31-Dec-2024 | 50 | This is required for T&F, IOPP and DOVE workflows. Other Production DUs are also asking for Archival/Retrieval
 |  |  | Total Efforts |  | 145 | 

## Slide 13
OND'24 iWMS - Core feature milestone
S.No | Type | Milestone | Planned Start Date | Planned End Date | Total Effort in PDs | Why ?
6 | Core | ILancer Integration | 1-Nov-2024 | 31-Dec-2024 | 35 | Integration with iLancer is required for many WMS migrations
7 | Core | INLP Integration | 1-Nov-2024 | 29-Nov-2024 | 12 | Integration with iNLP is required for many WMS migrations
8 | Core | No correction Engine | 1-Nov-2024 | 31-Dec-2024 | 37 | No correction engine required for Issue workflows
9 | Core | No correction file movement | 1-Nov-2024 | 29-Nov-2024 | 20 | No correction file movement required for all WMS
10 | Core | Reset Option | 1-Nov-2024 | 31-Dec-2024 | 26 | Reset option required for all WMS
11 | Core | Order Inflow data | 1-Nov-2024 | 29-Nov-2024 | 10 | Order Inflow data required for all WMS
12 | Core | Tools upload for Prod. Tech | 1-Nov-2024 | 31-Dec-2024 | 20 | To provide provision for prodn. tech to upload the tools
13 | No Code Platform | Menu configuration and access | 1-Nov-2024 | 31-Dec-2024 | 15 | Configuration Module
 |  |  | Total Efforts |  | 175 | 

## Slide 14
OND'24- WMS Goals – 1 of 2
Type | Goals | OND'24 Target
KPI | System uptime | 99.5%
 | UAT Bugs (Current: 82 including PROD) - This is te KPI for SQA. This measurement is for recent project i.e projects released since Jan 2024. Team is analyzing the data and will come up with actual bug count for Jun, Jul and Aug. Based on that reduction targets for Sept, Oct, Nov and December can be decided. | Not more than 15% bugs found by SQA. (Not more than 45 for the quarter)
 | SQA Bugs ( Current: 401 ). This is a KPI for developers. This is dependent on the project size ( lines of code). The number of bugs are 191 found by SQA for Jan, Feb and Mar 2024. Since there is no major SQA involvement from April, we are taking the score of JFM. From Oct 2024 onwards, SQA is going to be fully onboarded for testing. | Further 25% reduction by 31-December. (Not more than 100 per month; total 300 for the quarter)
 | ICA (Current: 0) - This is data for Jun, Jul, Aug 2024. This is an KPI for Dev, Test and Production team ( as the production team does the UAT ). No ICA mapping for WMS (ICA is currently not raised in the system. We will capture the ICAs from October onwards to measure and agree to an absoulute number for Nov and Dec and forward) | Absolute number to be calculated in October, so that OND and JFM targets can be arrived at.
 | 2024. This is an KPI for Dev, Test and Production team ( as the production team does the UAT ), project managers and and everyone in the leadership team. No CCA mapping for WMS (CCA is currently not raised in the system. We will capture the CCAs from October onwards to measure and agree to an absoulute number for Nov and Dec and forward) | Absolute number to be calculated in October, so that OND and JFM targets can be arrived at.
 | Reopen ( Current: 47 ) - This is an KPI for Dev, Test, product managers and everyone in the leadership team. Definition of Reopen is that everything is working in UAT and not working in Live. | Further 25% reduction by 31-December. (Not more than 13 per month; total 36 for the quarter)

## Slide 15
OND'24- WMS Goals – 2 of 2 (Documentation)
S.No. | Documents required | Date
1 | Architecture Document | 07-Oct-24
2 | Integration touch Points | 20-Dec-24
3 | Process to be followed for configuration | 13-Dec-24
4 | Process to be followed for customization | 20-Dec-24
5 | DB relationship diagram | 22-Oct-24
6 | Test Data and Test Cases | 21-Oct-24
7 | Features of New WMS | 15-Nov-24
8 | Code Review Checklist | 15-Oct-24
9 | Coding Standards document | 15-Oct-24
10 | User Manual | 15-Nov-24
11 | Requirement Document Checklist | 15-Oct-24

## Slide 17
www.integranxt.com
iTracks 1. JAS’24 - Update
2. Review OND’24 Plan

## Slide 18
JAS '24 update- iWMS (Planned vs Actual)
Quarter | Category | Planned | Actual
JAS'24 | On-time delivery(Tracks) | 100% | 100%
 | Budget value (iWMS + iTracks) | 160.32L (WMS and iTracks) | 63.73 (till August)

## Slide 19
JAS '24 update– iTracks Delivery Goals
S.No | Type | Module | Goals | Efforts(Person days) | Status | Live date | Why?
1 | Migration | Finance (Phase 2) | To migrate and complete the development of the Finance module in the iWMS system. (remaining 70% to be dev.) | 96 | 100 % completed Unplanned- Spilled Over to OND'24 | 30th Oct 2024 | Migrating Finance modules due to de-commission of iTrack in 2025.
3 | Migration | Non-WMS Customer onboarding screens (Phase 1) | To migrate the basic feature of existing iTracks so that non- WMS customer can be onboarded to iWMS | 111 | Planned for 40% completion in JAS'24 (Dev start date-22 July) | 1 Nov 2024 (phase1) | To migrate all the modules of the existing iTracks to the new system
 | Total efforts |  |  | 207 person days |  |  | 
Unplanned items-
New feature request- Re design review RFI workflow. This req. was shared to products team on 12th Aug 2024
Dev start - 30/9/2024 Dev End date- 25/10/2024

## Slide 20
www.integranxt.com
iTracks
Review OND’24 Plan

## Slide 21
OND'24 Update -(Planned vs Actual)
Budget | Planned
Budget Value (iWMS +iTracks ) | 162.95L
Budget Person days (iWMS +itracks) | 2073

## Slide 22
OND '24 update– iTracks Delivery Goals
S.No | Type | Module | Goals | Efforts(Person days) | Live date | Why?
1 | Migration | Finance (Phase 3) | Generate invoices and view UBR values from Odoo for customers migrated to the new WMS and newly migrated iTracks customers. 2. View Order inflow report from new iTracks for, ACS, CUP, Springer, WKH, T&F | 86 | Goal 1: 25th Nov 2024 Goal 2: 27th Dec 2024 | New Feature – Review RFI Raise RFI to Odoo for invoice generation Collect data from Odoo once invoiced to customer
3 | Migration | Non-WMS Customer onboarding (Phase 1-remaining 60% and Phase 2- 100% ) | Migration from old iTracks to new iTracks- (DU List) Academics Data conversion Pearson | 162 | 31st Dec 2024 | To migrate old iTracks customers to new iTracks system
 | Total efforts |  |  | 248 person days |  | 

## Slide 23
OND'24 -: Core team capacity and sprint plan
Resource | Count | Capacity (Person days) | Remarks
Developers | 4 | 240 | Suradha Vignesh Nirmala Chandrin
Tester | 1 | 60 | Gautham
Total Capacity(Dev. And Testing) | 5 | 300 | 
Product Management | 1.4 | 84 | Priya Alison
Dev. Lead | 1 | 60 | Mohan
QA Lead | 1 | 7 | Murali
Delivery Manager | 1 | 7 | Senthil
Grand Total | 9.4 | 458 | 

## Slide 24
OND'24 - Plan for Finance (Phase 3)
e | Epic | Development | Testing | Efforts in Person days | Sprint | Planned Start Date | Planned End Date | Go Live
Review Invoice (spill over from JAS'24) | Review Invoice – audit table Rejected RFI Completed RFI | 20 | 6 | 26 | S31,S32 | 30-09-2024 | 25-10-2024 | 30-10-2024
Odoo Integration UAT - Integra | Rate entry integration Invoice integration UBR integration 4. Queue status 5. Invoice Details 6. File Upload | 12 | 3 | 15 | S31 | 30-09-2024 | 18-10-2024 | 20-11-2024
 | Send Rejected RFI to new iTracks Sent Completed RFI to new iTracks | 10 | 3 | 13 | S33 | 28-10-2024 | 09-11-2024 | 11-09-2024
Validation Setup | Rate Entry Lock Job | 5 | 2 | 7 | S34 | 11-11-2024 | 22-11-2024 | 25-11-2024
Order inflow Report New iTracks | Send date from new to old iTracks to view order inflow Plan vs Actual Report for all customers Add items in Order inflow in new iTracks | 20 | 5 | 25 | S35,S36 | 25-11-2024 | 20-12-2024 | 27-12-2024
TOTAL |  | 67 | 19 | 86 |  |  |  | 

## Slide 25
ITracks- Finance Module (For invoice generation from Odoo)
Customer priority will be provided by Finance Team after batch 2 onwards
Batch | Type | DU List | Customer List | Invoice generation, UBR in Odoo (Go live) | Order inflow report in new iTracks
1 | New WMS | Editorial Services | ACS | 25th Nov'24 | 27th Dec'24
 |  | Journal Others | CUP |  | 
 |  | Journal Others | Wolters Kluwer Health |  | 
 |  | Springer | Springer |  | 
 | Old WMS | T&F | T&F |  | 
2 | Old iTracks | Academics | 11 customer | 16th Dec 2024 | 27th Dec'24
 |  | Data Conversion | 35 customer |  | 
 |  | Pearson | 6 customer |  | 

## Slide 26: OND'24- Non- WMS Customer Onboarding (Phase 1 completion)
Milestone# | Epic | Development | Testing | Efforts in Person days | Sprint | Planned Start Date | Planned End Date | Go Live date
New customer onboarding, Stages, Activity, Norms, Productivity | Stages Sub Jobs and Incoming | 12 | 4 | 16 | S30,S31 | 16/09/2024 | 11/10/2024 | 18 Oct 2024
Deliverables, UOM, Queries and checklist, Live Job | Production ¦ Live Jobs ¦ User Task creation Production ¦ Live Jobs Production and Customer dispatch Production ¦ Live Job ¦ Checklist | 12 | 4 | 16 | S31,S32 | 14/10/2024 | 25/10/2024 | 1 Nov 2024
 | Manual entry of logistics Miscellaneous entry Credit Hours Logistics Approval | 24 | 6 | 30 | S31,S32 | 30/09/2024 | 25/10/2024 | 1 Nov 2024
Total |  | 38 | 14 | 62 |  |  |  | 

## Slide 27: OND'24- Non- WMS Customer Onboarding (Phase 2)
Milestone# | Epic | Requirement | UX | Development | Testing | Efforts in person days | Sprint | Planned sprint start date | Planned sprint end date | Go Live
Deliverables, UOM, Queries and checklist, Live Job | Create Query Track Query Query Response | Completed | Completed | 9 | 3 | 12 | S33 | 28/10/2024 | 08/11/2024 | 18 Nov 2024
 | Checklist Master | Completed | Completed | 12 | 4 | 16 | S33 | 28/10/2024 | 08/11/2024 | 
Customer Migration Support | New WMS to Old WMS Integration Lead & Lag report Order Inflow dashboard OTD Report | NA | NA | 10 | 3 | 13 | S31 | 30/09/2024 | 11/10/2024 | 18 Oct 2024
Reports (Currently avail in old WMS) | 1.Build OTD Report | 15 Oct 2024 | 18 Oct 2024 | 20 | 5 | 25 | S33, S34 | 28/10/2024 | 08/11/2024 | 22 Nov 2024
 | 2. Build MIS Report | 15 Oct 2024 | 18 Oct 2024 | 20 | 5 | 25 | S33, S34 | 28/10/2024 | 08/11/2024 | 22 Nov 2024
 | 3. Build Delivery Report | 28 Oct 2024 | 30 Oct 2024 | 7 | 2 | 9 | S35 | 11/11/2024 | 22/11/2024 | 29 Nov 2024
Total |  |  |  | 78 | 22 | 100 |  |  |  | 
Remaining : 300(Total) - 248(Planned) = 52 days can be utilized for the below tasks:
Development of Non-WMS customer onboarding module phase 3
Customer migration form old iTracks to new iTracks for remaining DUs

## Slide 28
OND'24 - Migration Plan of customer to new iTracks
Remaining batches link: iTracks Module_Roadmap.xlsx (sharepoint.com)
Note: Upon the completion of Phases 1 and 2, the migration of customers from the old iTracks to the new iTracks will proceed without any development dependencies. Mohan and Priya will handle the configuration and setup for these customers.
Batch | DU | Customer count | Team Member | Customer onboarding phase 1 signoff | Customer onboarding phase 2 signoff | UAT Configuration date | UAT Testing Date (with DU) | Go Live
1 | Academic | 11 | Bagavathy, Dharanivel | 23-Aug-2024 | 08-Nov-2024 | 3rd Dec 2024 | 4th – 11th Dec | 31st Dec 2024
2 | Data Conversion | 35 | Bagavathy, Dharanivel |  |  |  |  | 31st Dec 2024
3 | Pearson | 6 | Renuga | 25-Sep-2024 |  |  |  | 31st Dec 2024

## Slide 29
iTracks – Backlog List
S.No. | Module | Milestone | Epics/Sub-Modules | Effort Estimation | 
1 | New WMS Customer Onboarding – Phase3 | Graphics | Graphic art cut list creation Graphic art cut list report Graphic art cut month wise report | 12 | 
 |  | Editorial Services | EPR Word count entry Despatches pages report`` | 5 | 
 |  | Create Reports in New iTracks- | Productivity and page target report Stage-wise detailed report Miscellaneous entry detailed report | 6 | 
 |  | Integrate new iTracks reports to iDashboard | OTD Report integration Order inflow report integration Delivery report integration | 10 | 
2 | Quality | Migration of remaining 4 sub modules | QTrack 7D Masters Checklist FQA |  | 
3 | Admin | Migration of 1 module | All Master Screen |  | 
4 | Vendor | Migrating the vendor module to iLancer – 2 module development | Vendor Vendor Report |  | 
5 | Finance | Migrating new iTracks customer to the finance module (UBR, Order Inflow and Invoicing) | Other Batch Customer Migration |  | 

## Slide 30
www.integranxt.com
iTracks Appendix

## Slide 31
Finance Module (Req. Closure Steps)
S.No | What was Done | Date
1 | During the Requirements Phase, we finalized the list of customers for migration and gathered the necessary invoicing inputs to be provided to Odoo | 13-June to 19- July
2 | First call with Odoo team – Presented the plan and the data required for the invoicing | 19-July-2024
3 | Products team technical discussion with Odoo | 26 to 27- July
4 | The Finance team has shared the requirements with the Odoo team regarding various invoice types and their respective fields. Odoo took time to analysis the requirement https://www.figma.com/board/rjQOCqjQbFYGyAqpMsOZFZ/Finance-Module-Workflow?node-id=69-204&node-type=shape_with_text&t=74rhf5H19ulrgvzz-0 | 1- Aug to 2- Sep
5 |  | 
6 | Sample JSON format sent from Odoo | 20-Aug
7 | Demo of the overall Masters and Configuration screen in Odoo | 2- Sep
8 | Odoo and Integra shared and reviewed the JSON format to cross-verify the inputs they would receive | 4-Sep - Ongoing
8 | Tentative Initial plan shared by Odoo | 3-Sep
9 | Ensuring a seamless transition for UBR, RFI, order inflow value from iTracks to Odoo. Discussion with Finance to confirm which DU batches should be included in the upcoming releases to align with the URB service values. | 9-Sep
10 | Sent an email to the Finance team requesting sign-off on the interim solution for the capturing UBR and Invoice descriptions. Also requested the batch list for migrating customers to the new iTrack module – currently awaiting a response. | 16-Sep
11 | Revised plan shared by Odoo | 18-Sep

## Slide 32
JAS'24 - Plan for Finance (Phase 2)
Milestone# | Epic | Development | Testing | Efforts in Person days | Sprint | Planned Start Date | Planned End Date | Status | GoLive
Order Inflow / Rate Entry (70% - 30% was developed in previous quatre) | Journal Rate Entry Project Rate Entry Order inflow Configuration | 18 | 6 | 24 | S25,S26, S27 | 08/07/2024 | 16/08/2024 | Completed 100% UAT in progress | 30/09/2024
RFI (Rate integration) | Invoicing Configuration Raise RFI RFI Rejection | 14 | 5 | 19 | S26,S27, S28, S29, S30 | 22/07/2024 05/08/2024 | 13/09/2024 27/09/2024 | Testing in progress | 3/10/2024
Review Invoice (Unplanned) | Review invoice (partial) | 25 | 9 | 34 | S30, S31, S32 | 16/09/2024 | 25/10/2024 | In Progress(Spill over to OND) | 30-10-2024
Lock Job | Lock/ Unlock | 3 | 1 | 4 | S26,S27 | 22/07/2024 | 2/07/2024 16/08/2024 | Completed 100% UAT in progress | 30/09/2024
Odoo Integration - Integra | Create integration component- Rate Entry, Invoice integration, UBR integration | 10 | 6 | 18 | S30, S31 | 16/09/2024 | 11/10/2024 | In progress | 20-11-2024
TOTAL |  | 61 | 22 | 83 |  |  |  |  | 

## Slide 33
JAS'24 - Plan for Finance (Phase 2)
*Reports- Order inflow report is partially completed (quantity needs to be fetched from WMS)- Dependency on WMS
Milestone# | Epic | Requirement | UX/UI | Development | Testing | Efforts in Person days | Sprint | Planned Start Date | Planned End Date | Status | GoLive
Odoo Integration - Odoo | Invoice Generation UBR syncing with invoice (service wise) | Completed | NA | ODOO | ODOO | ODOO | ODOO | ODOO | 20/11/2024 (Date by Odoo) | In progress | 20-11-2024
Reports | Order Inflow report Plan VS Actual report | 26-7-2024 31-7-2024 | 2-7-2024 31-7-2024 | 10 | 3 | 13 | S28, S29, S30 | 19/08/2024 | 13/09/2024 27/09/2024 | Order inflow report completed - UAT to be given* | 27-12-2024
TOTAL |  |  |  | 10 | 3 | 13 |  |  |  |  | 

## Slide 34
JAS'24 update- Plan for Non-WMS Customer onboarding screen (Phase 1)
Milestones | Epic | Requirement | UI/UX | Development | Testing | Efforts in Person days | Sprint | Planned Start Date | Planned End Date | JAS Status | Go Live
Work order management | 1.Customer and Work order customization 2. Workorder creation | 5 July 2024 28 June 2024 (Batch 1,2) | 28 June 2024 | 16 | 5 | 21 | S26,S27,S28 | 22/07/2024 | 30/08/2024 | Completed 100% UAT in progress | 30 Sep 2024
New customer onboarding Stages, Activity, Norms, Productivity | 3. Stages and Lot 4. Sub Job and Incoming |  | 28 June 2024 | 12 | 4 | 16 | S28,S29 S30,S31 | 19/08/2024 16/09/2024 | 13/09/2024 11/10/2024 | In Progress (Delay because of change in workflow) | 18 Oct 2024
 | Total |  |  | 28 | 9 | 37 |  |  |  |  | 

## Slide 35
JAS'24 Update-Plan for Non-WMS Customer onboarding screen (Phase 1)
Milestone# | Epic | Requirement | UI/ UX | Development | Testing | Efforts in Person days | Sprint | Planned Start Date | Planned End Date | Status | Go Live
Deliverables, UOM, Queries and checklist, Live Jobs | 5. Production ¦ Live Jobs ¦ User Task creation 6. Production ¦ Live Jobs ¦Production and Customer dispatch 7. Production ¦ Live Job ¦ Checklist | 12 July 2024 30 July 2024 (Batch 1,2) | 5 July 2024 31 July 2024 13 Aug 2024 | 12 | 4 | 16 | S29,S30,S31 | 02/09/2024 | 11/10/2024 | In Progress | 18 Oct 2024
 | 11. Manual entry of logistics 12. Miscellaneous entry 13. Credit hours 14. Logistics approval | 12 July 2024 31 July 2024 (Batch 1,2) | 31 July 2024 13 Aug 2024 | 24 | 6 | 30 | S29,S30,S31, S32 | 16/9/2024 2/09/2024 | 25/10/2024 | In Progress | 1 Nov 2024
TOTAL |  |  |  | 36 | 10 | 46 |  |  |  |  | 
Remaining : 305(Total) - 207 (Planned) = 98 days can be utilized for the below tasks: ​
Production module phase 2 dev.​
iAspire post implementation support​

## Slide 36
Validation Pointers for Finance Module in WMS System
Rate Entry Validation - this needs to be by iTracks for the new WMS migrating customers.
  For Journals: The rate entry for journals- All stages needs to be done in advance. The system should restrict the creation of a Work Order for a journal until the rate entry is completed.
  For Books: The system should validate if the rate entry is completed for a predefined stage. If the rate entry is not done, then user will not be able to access the stage and alert will be triggered.
Lock Job Validation - needs to be developed in new iTracks
  A job can only be locked within the system once a full invoice has been invoiced in odoo and sent to customer. If the invoicing is partial, the system should alert the user, that they cannot lock the job until full invoice are raised.
  Raise RFI Touchpoints – There will be only certain fields where the PM would be adding to RFI manually

## Slide 37
In agreement with Finance team (Internal)
Unbilled Revenue (UBR)
Current Implementation: Odoo has been integrated with UBR for some DUs- full invoice data for books, journals, and data conversion. However, for full invoices the service category is not captured in Odoo, since service wise bifurcation is not present in the old iTracks.
Missing in Current UBR Implementation: Integra is not pushing partial invoice data to Odoo for UBR because the old system does not capture the billable service-wise details (CUP can be implemented without partial invoice).
Proposed System: To ensure accurate UBR adjustments, the UBR modifications can only be made after the corresponding invoice is captured in Odoo. But this will take time, since we are developing invoice module in the new iTracks and Odoo.
  As per what is already developed for UBR- we will be sending the full invoice data from old iTracks to odoo(without service bifurcation)
  For a temporary solution, we suggest, to push the partial invoice data from old iTracks to Odoo (without service bifurcation) to avoid any dev effort of team on old iTracks.
  This will allow for UBR value adjustments to be made based on both full and partial invoices.
  This was discussed and agreed by Prabakaran and Saravanan on 11th Sep.
    Once the invoice generation for a DU is completed in the new iTracks and Odoo, then we can start pushing invoice for both partial and full with service bifurcation from new iTracks to Odoo.

## Slide 38
In agreement with Finance team (Internal)
Invoice Generation
Manual Billing:
  For every DU and customer as per the workflow configuration in the new WMS, once the respective stage is completed, the job will move into the invoice queue (Rasie RFI).
  At this point, the Project Manager will manually verify the services (all services will be listed as provided in the Rate Entry screen), Invoice Description(the invoice description should be provided in the Finance Configuration screen so that it will auto populate in the raise invoice page for a job card); input the PO number, and push the invoice data for review to the PM-TL
  The PM-TL will review the invoice information and manually push (by approving the RFI) the data to Odoo.
Batch 1 (Manual billing Customers)-
  ACS, Springer, CUP: Article wise data will be sent from the new iTracks system to Odoo.
  WKH and CUP (Issue Workflow): Currently, the issue workflow is not available in the new WMS system.
    In the new iTracks , PM will manually create issues in the "Raise RFI" screen and add relevant article and will send the information to Odoo.
    As discussed on 12th Sep call with Odoo, the New iTracks will send issue information to Odoo, (the issue will include the article details such as article ID, services, quantity, and rates). Mohan, Prabakaran and the Odoo team has agreed that iTracks will send the article information as an issue to Odoo and Odoo will process it to generate cumulative issue invoices for customers.

## Slide 39
In agreement with Finance team (Internal)
Automatic Billing (T&F in Batch 1): For T&F, we will send the data from the old system via API to Odoo.
  Invoice Description:
    In the old system, there is a logic for the automatically creating invoice description which gets added to the raised invoice.
    This logic is not present in the new iTracks, as discussed and agreed with Finance team.
  For the current invoice generation for T&F, we will be passing the invoice description along with invoice details to Odoo from the old iTracks only -
  Mohan needs to update the JSON for T&F to add the invoice description information from old iTracks.
  Future Development: Once T&F is migrated to the new WMS system, this invoice description generation functionality will need to be implemented within the new iTracks system as well .
Note : The invoice description is already developed in the new iTracks system for customers with a static invoice description, the data will appear on the RFI screen without requiring any development. However, if a customer's invoice description involves a combination of volume, issue, or any other variable, custom development will be needed to migrate the customer.

## Slide 40
www.integranxt.com
WMS Appendix

## Slide 41: WMS – AMJ
Version 1.0
03-Jul-24

## Slide 42: WKH | Bug & Enhancement Points
Sl. No | Division | Stage | Improvement Points | DU | Type | Action | Target Date | Details
1 | US | Issue Proof | Issue Proof 1: Develop a method to handle Issue Proof 1 in WMS. | WMS/TANDE | Enhancement | Development in progress | 14-Aug | T&E Signoff rec.
2 | US | Issue Revises | Issue Revises: Ensure the inclusion of all necessary revisions for issues. | WMS/TANDE | Enhancement | Development in progress | 14-Aug 16-Sep | T&E Testing completed
3 | US | Finals | Printer and SSR Handling: Develop printer and SSR in WMS | WMS/TANDE | Enhancement | Development in progress | 14-Aug 20-Sep 5-Oct | Delay
4 | US | All | Live Production WIP: Required article wise due date for all stages | WMS | Enhancement | Need to Develop | 09-Sep 14-Oct | Reopen
5 | US | PAP | PAP – Online QC provision yet to provide | WMS | Enhancement | Need to Develop | 14-Sep | T&E Signoff
6 | US | PAP | PAP – Journal Specific requirement not covered in workflow (3 journal publication date to be added in PDF) - No provision given | WMS | Enhancement | Need to Develop | 14-Sep | Delay
7 | US | PAP | Revised PAP: No stage provided in WMS | WMS | Enhancement | Need to Develop | 30-Sep 14-Oct | Delay
8 | US | PAP | Revised PAP: No provision given to handle the application within PAP process | WMS | Enhancement | Need to Develop | 30-Sep 12-Oct | 6 and 7 both same point Duplicate
9 | US | First Proof | First Proof: PreProof Completion should not be mandate process in WMS | WMS | Enhancement | Need to Develop | 16-Sep | Completed
10 | US | Pre Proof | Pre Proof: Should be made configurable in Journal Master | WMS | Enhancement | Need to Develop | 16-Sep | Not required
11 | US | Revised FP | Revised First Proof: Not defined in WMS | WMS/TANDE | Enhancement | Need to Develop | 16-Sep 30-Sep YTD | Low Priority
12 | US | Revises | Revises-1: Due to challenges in First Proof workflow definition Revises is not enabled in WMS | WMS | Bug | FTP package need to map | 16-Sep | Completed
13 | US | Revises | Revises-2: Workflow not defined in WMS | WMS | Bug | FTP package need to map | 16-Sep | Not Required Completed
14 | US | General | Information to PME: No provision provided in WMS to pass any information to PME during dispatch | WMS | Enhancement | Need to Develop | 22-Oct | 
15 | US | General | Reset Option: Establish a method for managing reset options within the workflow. | WMS | Enhancement | Need to Develop Core | 30-Nov | 
16 | US | General | No Correction: Article with no correction is not handled in WMS | WMS | Enhancement | Need to Develop Core | 30-Nov | 
17 | US | All | Auto Archival: Implement an auto-archival feature for completed articles. | WMS | Enhancement | Need to Develop | 31-Dec | 
18 | US | All | Configurable journal master not provided (i.e CE review update, routing article through internal/External CE, Journal which does not have PAP stage, Early access date for specific journals) | WMS | Enhancement | Need to Develop | 31-Oct | 
19 | UK | Revises | New Requirement: In UK we need to deliver the Revises and PAP in Revises stage itself. Provision to be given to handle PAP package creation and uploading based on UK division | WMS | Enhancement | Need to Develop | 31-Oct | New Addesd
20 | US | All | PDF Compare: Compared PDFs not saved in WMS | WMS | Bug | Need to Check | NA | iNet PDF compare have link only
21 | US and UK | First Proof | Order Inflow capturing issue | WMS | Bug | Need to Check | 31-Oct | 
22 | UK | PAP (Post Accept) | Need to provide a workflow to process post acceptance task (similar to PAP of OUP journals) | WMS | Enhancement | Need to Check | 30-Nov | New Reqmnt

## Slide 43: CUP-Journals| Bug & Enhancement Points
Sl. No | Request Placed on | Description | Priority | Remarks | Type | Target Date | Production remarks
1 | Nov-23 | Issue workflow in iWMS | P1 | Long pending. Issue workflow confirmation given by Murugan to WMS team. Need to prioritize. | Enhancement | YTP. We will provide target date by 16th Oct | 
2 | Mar-24 | Revised proof email notifications for ANR, APL, LPB (revised proofs should be sent to corresponding author) & 2 step revised proofs delivery. 1st round author/editor and 2nd round to CM upon approval for few journals Should be given as configurable model in journal master | P1 | This request was pending from March'24. The revised proof for all these 3 journals should be sent to Corresponding Author, CC to Content Manager and BCC to Aboo | Enhancement | 19-Aug-24 16-Sep-24 30-Sep-24 14-Oct-24 | Not yet implemented. Revised target date 2nd Sept is not met as well. Delay
3 | Nov-23 | First View Package creation automation (should be engine based activity) | P1 | Currently is being done manually taking more time. This automation is still in discussion. WMS team to discuss with production technology (Kannika & Team) and take it forward. | Enhancement | 23-Sep-24 YTD | New Engine not received
4 | Mar-24 | Query Module implemented, but demo not provided to PM/Prod, so unable to use the functionality | P1 | Need support from WMS team. | Enhancement | 30-Oct-24 17-Sep-24 | We will provide current system demo by 16th Sep. Demo Provided received feedback and it has been updated. Revised demo will be provided on 17th Sep 2024 Demo Provided
5 | Sep-23 | Erratum, Addendum and Corrigendum article type handling in iWMS (currently not ingested in WMS) | P1 | Metadata will not have email id information. Apart from this, all information will be given in the Metadata XML. Task to be initiated based on the receipt. Author proof emails should not be triggered, instead proof notification should be sent to PM (Aboo) | Enhancement | 15-Dec-24 | 
6 | Mar-24 | Revised first view stage not enabled in WMS automatically First view resupply – Auto initiation and task re-route to Composing – Capture email as input file (either HTML/notepad) | P2 | Resupply is triggered based on the email notification. However, we need the notes for resupply to be included. Please refer attached samples. | Bug | 31-Dec-24 | 

## Slide 44: CUP-Journals| Bug & Enhancement Points
Sl. No | Request Placed on | Description | Priority | Remarks | Type | Target Date | Production remarks
7 | Mar-24 | Productivity Report | P2 | Internal use | Bug | 23-Sep-24 23-Oct-24 | 
8 | Nov-23 | Pending option required for iAutopagination | P1 | If any files are rejected during iAutopagination, we need pending option for user task. | Bug | 23-Sep-24 | Completed
9 | May-24 | Overall OTD calculation report + Article stage tracker details needed (reporting based on customer request) | P1 | External use. This is required for generating Monthly report which is sent to the customer. | Bug | 30-Sep-24 YTD | 
10 | May-24 | First view activity is currently closed based on success of uploading the files from user machine to iCloud, whereas it should be closed only if it is successfully uploaded to customer ftp from iCloud | P1 |  | Bug | 30-Sep-24 14-Oct-24 | 
11 | Recurring | Engine activities (XML CONVERSION & iAuto Pagination) not working | Lag | Recent issue | Bug | 30-Sep-24 | Completed
12 | Recurring | Double entry shows in incoming inspection activity for few articles | Lag | Recent issue | Bug | 30-Sep-24 14-Oct-24 | 
13 | May'24 | In Revises 2 stage, Rejection option required for online QC (in case any errors has been identified by XML operator). Provisions available in Revises 1 stage | P3 | Self-explanatory | Enhancements | 20-Oct-24 | 
14 | Mar'24 | iTracks integration with journal master – Currently journal master is created twice | P3 | Dual configuration required (iTracks and WMS). Need integration / syncing | Enhancements | 15-Nov-24 | 
15 | Recurring | In revises stage, iPub suite link not opening via iWMS for QC/FQA (User manually opening in chrome) | Lag |  | Bug | 15-Nov-24 | 
16 | Recurring | PDF compare link opening twice in QC stage | Lag |  | Bug | 15-Nov-24 | 
17 | Recurring | Multiple Pop- Up error occurs | Lag |  | Bug | 15-Nov-24 | 
18 | Jan-24 | Displaying pending/hold remarks in the my task page – long pending request | P3 | For pending articles, the remarks should be displayed under 'My Task' | Enhancements | 15-Nov-24 | 
19 | May'24 | Task differentiation for PM rejection and regular FQA process | P3 | Need to differentiate task between FQA and PM rejection | Enhancements | 15-Nov-24 | 
20 | Mar-24 | Accepted Manuscript Workflow not provided in WMS | P3 | Self-explanatory. S5 or PAP-A stage to be initiated based on the mail subject. | Enhancements | 31-Dec-24 | 
21 | Recurring | File not ingested in iWMS | Lag |  | Bug | Closed | Reopen

## Slide 45: ACS| Bug - Points
Sl. No | Priority | Description | Target Date | Remarks
1 | P1 | iCore to ACS XML engine delays: iCore files of the copyedited files are not moved to XML activity. Files are currently moved with the help of HelpDesk team. | 30-Sep-24 23-Sep-24 | Completed in observation
2 | P1 | iCore to ACS XML' failure cases are moved to 'XML viewing & validation' activity without the output ACS XML file. The system should move the failure cases to 'iCore to ACS XML_F'. | 30-Sep-24 23-Sep-24 | Completed
3 | P1 | ACS XML files are not moved to 'Dispatch' activity after the completion of 'XML viewing & validation' activity. | 30-Sep-24 23-Sep-24 | Completed in observation
4 | P1 | Level of edit/grammar score: The data is not shown in the extracted Excel report. | 30-Sep-24 | Completed
5 | P1 | “Revises iteration” error while opening files in WMS | 30-Sep-24 12-Oct-24 | 
6 | P1 | Delivery monitoring report: Only date is shown not the time; when extracted to Excel, the same time is shown for all. | 30-Sep-24 | Completed
7 | P1 | File status: For some articles, start & end time shows the same time with ‘0’ time taken; status shows ‘Work In Progress’ for the completed articles. | 30-Sep-24 | Completed
8 | P2 | The iAuthor link does not open on clicking 'iAuthor Viewer' for 'pending' articles. Need to open from “tool status” by clicking on “Click here” option in remarks | 30-Oct-24 | 
9 | P2 | Dispatch transaction XML’s request ID for the Error Handling-raised articles should be the request ID in the ACS’s Error-Handling transaction XML | 30-Oct-24 15-Oct-24 | 
10 | P2 | Job not created – For some articles, job transfer is not done even after 24 h of receipt of the articles from ACS (refer to the attached email ‘an4c03925…’). | 30-Oct-24 | 
11 | P3 | WIP report: Input Type shows 'Edited Word file & TEX file' for all the articles. It should be 'Word' for Word files and 'LaTex' for LaTex files. | 30-Nov-24 | 
12 | P3 | Unable to close the WMS window using 'sign out' or close buttons. Users need to give 'End Task' in the Task Manager. | 31-Dec-24 | 
13 | P3 | Unable to reset files to previous stages | 31-Dec-24 | 
14 | P2 | Level of edit/grammar score: The data shown in the WIP report is incorrect | Closed | 

## Slide 46: ACS| Requirement - Points
Sl. No | Priority | Description | Target Date | Remarks
1 | P1 | iNLP workflow integration | 13-Sep-24 YTD | Completed in WMS. Pending in iAuthor. Revised date to be received from iAuthor
2 | P1 | iPubEdit4.0 implementation for the initial conversion stage | 16-Sep-24 YTD | Based on production UAT Completion
3 | P2 | File status: need an option to download all the files listed under 'Files' tab. | 15-Oct-24 | 
4 | P2 | Error handling: Auto-email to be triggered on receipt of error handling response from ACS | 03-Nov-24 | 
5 | P2 | Error handling: query status (open/closed) should be shown in the WIP report | 03-Nov-24 14-Oct-24 | 
6 | P2 | OTD report: The due date should be calculated based on the level of effort (LoE; level 0, 1, 2 and 3). The report should be linked to iDashboard. | 03-Nov-24 | 
7 | P2 | Graphics spell-check tool should be integrated into the new WMS | 30-Nov-24 30-Oct-24 | 
8 | P3 | Need a report to view the <noteFromVendor> text provided for the articles. | 30-Nov-24 | 
9 | P3 | Word-count tool needed to show the word-count (with and without references) of the articles processed in iPubEdit4.0. This data should be displayed in the WIP report. | 30-Nov-24 30-Oct-24 | 
10 | P3 | Productivity not captured in iTracks and iAspire. | 30-Dec-24 | 
11 | P3 | ‘Do not publish’ window: Should be displayed to the users and the content should be added to the final ACS transaction XML | 30-Dec-24 | 
12 | P3 | Checklist should be integrated into WMS on save activity. Option to view the saved checklists is also needed. | 30-Dec-24 | 
13 | P3 | If image validation failed, graphic activity should be automatically reset to YTS. If success, graphic & conversion dispatch should be enabled automatically. | 30-Dec-24 | 
14 | P3 | WMS: auto-archival of 6-month-old files | 30-Dec-24 | 

## Slide 47: CUP-Journals| Copyediting| Outstanding Points
Sl. No | Priority | Category | Description | Target Date | Remarks
1 | P1 | Bug | While running “Compare Document”, the following error pops out (frequently). Moreover, we are unable to close this and forced to give 'End Task' from the Task Manager. | 30-Sep-24 14-Oct-24 | 
2 | P2 | Enhancement | “Reject” option to be added | 15-Oct-24 | 
3 | P2 | Enhancement | “Due date” in WMS mismatches the correct CE due date (+1 day from the day TE is done). If first proof due date, please specify. | 15-Oct-24 | 
4 | P2 | Enhancement | Journal type needs to be mentioned: Onshore/Offshore, etc. | 15-Oct-24 | 
5 | P2 | Enhancement | Complexity to be mentioned: Level I/Level II | 15-Oct-24 | 
6 | P3 | Enhancement | Copyediting queue | 23-Dec-24 | 
7 | P3 | Enhancement | Word count (with and without references) of the articles should be displayed in the iWMS. | 23-Dec-24 | 

## Slide 48: WKH| Copyediting| Outstanding Points
Sl. No | Priority | Category | Description | Target Date | Remarks
1 | P1 | Enhancement | Exact due date is not being correctly listed in WMS | 16-Sep-24 14-Oct-24 | Reopen
2 | P2 | Bugs | "Compare Document" is not working properly; we have click at least 3 to 4 times for this macro to work | 15-Oct-24 | 
3 | P2 | Enhancement | Integrate the data in copyediting queue to WIP report | 30-Nov-24 | 
4 | P2 | Enhancement | Word count (with and without references) of the articles should be displayed. | 30-Nov-24 30-Oct-24 | 
5 | P2 | Enhancement | “Reject” option to be added b/w stages (L2 to L1) | 30-Nov-24 | 
6 | P2 | Enhancement | Package creation stage to be made automatable | 30-Nov-24 | 
7 | P2 | Enhancement | Query module has not been integrated | 30-Nov-24 | 
8 | P3 | Enhancement | Need different tabs for different reports: for example, we should be able to see File Status and WIP report at the same time in different tabs | 31-Dec-24 | 
9 | P3 | Bugs | Filter for WIP report is not user friendly for all columns as dropdown is not shown | 31-Dec-24 | 

## Slide 49
CORE | Backlog Modules to be Developed
Archival / Retrieval – Planned in OND
WMS Engines Development – Currently using Old WMS Engines – Development in Progress |Target Date: YTD
No Code Platform – Development In Progress
Adaptors Library
Peer Review Core Module (WKI PRS can be reused)
Manuscript Submission (Bloomsbury can be reused)
Dynamic Reports
Complete plan and Resource requirements for pending modules and No Code platform will be shared in a separate call